## General Management
General Management Activities
FY19 | Prepare and submit FR for next year of 128(a) | Prepare and submit quarterly progress report (QPR) #1 | Prepare and submit QPR #2 and success story | Prepare and submit QPR #3 | Prepare and submit QPR #4 / Success Story/Final Progress Report (FPR) |  |  | Attend Alaska Tribal Conference on Environmental Management to build knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | Attend ITEP’s Tribal Lands and Environment Forum to build knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | Update administrative TRP as needed. | Purchase supplies/equipment as needed. | [9 empty] | Practice environmentally friendly workplace procedures. (E.g. ride-sharing with co-workers to meetings, recycling, printing on both sides of paper, minimizing packaging on purchased supplies, no single use plastics for outreach, following our green cleaning policies for CVTC.)
FY20 | Prepare and submit FR for next year of STRP 128 (a): Update workplan to show how the Tribe wants to grow the program in the coming year | Prepare and submit quarterly progress report (QPR) #1 | Prepare and submit QPR #2 and success story | Prepare and submit QPR #3 | Prepare and submit QPR #4 / Final Progress Report (FPR) and success story |  |  | Attend Alaska Tribal Conference on Environmental Management (ATCEM) to build knowledge of brownfields, TRP management, environmental assessment, and cleanup actions. | Attend ITEP’s Tribal Lands and Environment Forum to build knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | Update administrative TRP manual as needed. | Purchase supplies/equipment as needed following EPA R10 STRP 128 (a) guidelines. | Attend training and webinars pertinent to brownfields and spill response | Attend QAPP Training
FY21 | Prepare and submit FR for next year of STRP 128 (a): Update workplan to show how the Tribe wants to grow the program in the coming year | Prepare and submit Quarterly Progress Report (QPR) #1 | Prepare and submit QPR #2 and Success Story | Prepare and submit QPR #3 | Prepare and submit QPR #4 / Final Progress Report (FPR) and Success Story |  | Update Work Plan (as appropriate) | Attend Alaska Tribal Conference on Environmental Management (ATCEM) to build knowledge of brownfields, TRP management, environmental assessment, and cleanup actions. Specific focus: writing Phase I ESAs | Attend ITEP’s Tribal Lands and Environment Forum to build knowledge of BFs, TRP management, environmental assessment, and cleanup actions. Specific focus on writing Phase I ESAs. | Update administrative TRP manual as needed. | Purchase supplies/equipment as needed following EPA R10 STRP 128 (a) guidelines. | Attend training and webinars pertinent to brownfields and spill response | Attend QAPP Training | Maintain Work Log | Cross training of other CVTC staff members so that all knowledge from TRP program will not be lost in any possible staff change.
FY22 | Prepare and submit FR for next year of STRP 128 (a): Update workplan to show how the Tribe wants to grow the program in the coming year | Prepare and submit Quarterly Progress Report (QPR) #1 | Prepare and submit Quarterly Progress Report (QPR) #2 and Success/Accomplishment Story | Prepare and submit Quarterly Progress Report (QPR) #3 | Prepare and submit Quarterly Progress Report (QPR) #4/Final Progress Report, Federal Financial Report (FFR) & Success/Accomplishment Story |  | Update Workplan (as necessary) | Attend Alaska Tribal Conference on Environmental Management (ATCEM) to build knowledge of brownfields, TRP management, environmental assessment, and cleanup actions. | Attend ITEP’s Tribal Lands and Environment Forum to build knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | Update administrative TRP manual as needed. | Purchase supplies/equipment as needed following EPA R10 STRP 128 (a) guidelines. | Attend training and webinars pertinent to brownfields and spill response | Attend QAPP Training | Maintain Work Log | Cross training of other CVTC staff members so that all knowledge from TRP program will not be lost in any possible staff change. | Attend the Alaska Forum on the Environment Conference to build knowledge pertaining to brownfield concerns in Alaska, contamination concerns, and cleanup actions.
FY23 | Prepare and submit FR for next year of STRP 128 (a): Update workplan to show how the Tribe wants to grow the program in the coming year | Prepare and submit Quarterly Progress Report (QPR) #1 | Prepare and submit Quarterly Progress Report (QPR) #2 | Prepare and submit Quarterly Progress Report (QPR) #3 | Prepare and submit Quarterly Progress Report (QPR) #4/Final Progress Report, Federal Financial Report (FFR) & Success/Accomplishment Story |  | Update Workplan (as necessary) | Attend Alaska Tribal Conference on Environmental Management (ATCEM) to continue building knowledge of brownfields, TRP management, environmental assessment, and cleanup actions. | Attend ITEP’s Tribal Lands and Environment Forum to continue building knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | Update administrative TRP manual as needed. | Purchase supplies/equipment as needed following EPA R10 STRP 128 (a) guidelines. | Attend training and webinars pertinent to brownfields and spill response | Attend QAPP Training | Maintain Work Log | Cross training of other CVTC staff members so that all knowledge from TRP program will not be lost in any possible staff change. | Attend the Alaska Forum on the Environment Conference to continue building knowledge pertaining to brownfield concerns in Alaska, contamination concerns, and cleanup actions. | Attend the Alaska STRP Workshop to continue building Alaska-specific knowledge pertaining to brownfield concerns, contamination concerns, cleanup actions, and specific training for Alaska TRP Coordinators.
FY24 | Prepare and submit FR for next year of STRP 128 (a): Update workplan to show how the Tribe wants to grow the program in the coming year | Prepare and submit Quarterly Progress Report (QPR) #1 | Prepare and submit Quarterly Progress Report (QPR) #2 | Prepare and submit Quarterly Progress Report (QPR) #3 | Prepare and submit Quarterly Progress Report (QPR) #4/Final Progress Report, Federal Financial Report (FFR) & Success/Accomplishment Story | Submit PALs for FY25 | Update Workplan (as necessary) | Maintain Monthly Work Log describing work the TRP Coordinator accomplishes daily. This information is then used to write the QPRs. | Update administrative TRP manual as needed. | Develop/maintain a “Four Elements Summary Sheet” for TRP Manual to record important wording with partner agencies (e.g. federal and state agencies, TAB partners, etc.) as we as record acceptable activities/tasks that meet the requirements of each element of a STRP 128(a) program. | Attend training and webinars pertinent to brownfields and spill response | Purchase supplies/equipment as needed following EPA R10 STRP 128 (a) guidelines in the approved Work Plan, or with permission from EPA PM prior to purchasing. | [Trip A]Attend Alaska Tribal Conference on Environmental Management (ATCEM) to continue building knowledge of brownfields, TRP management, environmental assessment, and cleanup actions. | [Trip B]Attend ITEP’s Tribal Lands and Environment Forum to continue building knowledge of BFs, TRP management, environmental assessment, and cleanup actions. | [Trip C]Attend the Alaska Forum on the Environment Conference to continue building knowledge pertaining to brownfield concerns in Alaska, contamination concerns, and cleanup actions. | [Trip D]Attend the Alaska STRP Workshop to continue building Alaska-specific knowledge pertaining to brownfield concerns, contamination concerns, cleanup actions, and specific training for Alaska TRP Coordinators. | [Trip E]Attend the National Brownfields Training Conference to continue building knowledge pertaining to brownfield concerns, contamination concerns, cleanup actions, and , other relevant learning experiences as well as peer-to-peer networking with colleagues from the Lower 48 | [Trip F]Attend the Pacific Northwest Training/Workshop/Conference which will help enhance the Chickaloon TRP through networking and learning from other tribes in Region 10. When the training is formally announced, the Chickaloon TRP will get approval to attend from the EPA PO and get more accurate information for the budget category. | Attend QAPP Training | Cross training of other CVTC staff members so that all knowledge from TRP program will not be lost in any possible staff change.
FY25

## Element 1
Element 1 Activities
FY19 | Update CVTC website with estimated or known BF sites. | Follow up with any community members who reach out with a site of concern. | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | Prepare and submit eligibility forms or request TBA or DBAC services for sites. | Review state and other sites for updated information on any locally relevant cleanup or contaminated sites. | Review of site inventory to identify candidate sites for reuse. | Work with CVTC Health and Social Services Department to visit with Elders and learn of history of local area and sites of potential concern.
FY20 | Update CVTC website with suspected or known BF sites. | Follow up with any community members who reach out with a site of concern. | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | Prepare and submit eligibility forms or request TBA or DBAC services for sites. | Review state and other sites for updated information on any locally relevant cleanup or contaminated sites. | Review of site inventory to identify candidate sites for reuse. | Prioritize sites on CVTC brownfield inventory: CVTC Land Use Committee recommendations developed and Council review/edits/approval of prioritized list | For the top five prioritized sites on the CVTC brownfield inventory: quarterly information gathering (if possible; minimum annual information gathering) including one on one interviews with local community members and other knowledgeable individuals; visit sites to develop written and photographic documentation of site conditions, and document location with GPS; discuss sites with STRP colleagues (including DEC, etc) for final determination of land status. | Occasionally attend Community Council meetings (Sutton, Chickaloon, Palmer) to learn about any areas of concern pertaining to BF issues | Update (as needed) site inventory, including use of a digital mapping system of the site inventory to visually (and geographically) explain sites of concern. | Develop a flow chart and associated written description of CVTC processes and tasks that are initiated with the report of a suspected or known contaminated site.
FY21 | Update CVTC inventory with suspected or known contaminated sites. | Follow up with any community members who reach out with a site of concern. | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | Prepare and submit eligibility forms or request TBA or DBAC services for sites. | Review state and other sites for updated information on any locally relevant cleanup or contaminated sites. | Review of site inventory to identify candidate sites for reuse. | Prioritize sites on CVTC brownfield inventory: CVTC Land Use Committee recommendations developed and Council review/edits/approval of prioritized list | For the top five prioritized sites on the CVTC brownfield inventory: quarterly information gathering (if possible; minimum annual information gathering) including one on one interviews with local community members and other knowledgeable individuals; visit sites to develop written and photographic documentation of site conditions, and document location with GPS; discuss sites with STRP colleagues (including DEC, etc) for final determination of land status. | Occasionally attend Community Council meetings (Sutton, Chickaloon, Palmer) to learn about any areas of concern pertaining to BF issues | TRP Manager and Contractor to create a digital mapping system of the site inventory to visually explain sites of concern. | Use developed flow chart and associated written description of CVTC processes and tasks that are initiated with the report of a suspected or known contaminated site to cross-train staff in TRP management. | CVTC will work with Native Village of Eklutna in our overlapping area. We will compare databases and work together on joint sites of concern. | For community members that come and request process information/money for cleanup of their site, help them prepare and submit eligibility forms or request TAB or DBAC services for sites. | A digital mapping system of the site inventory to visually (and geographically) explain sites of concern.
FY22 | Update a website or tracking system (Excel, paper files, etc.) with estimated or known BF sites. | Follow up with community members on sites of interest or concern (as available) | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | For community members that request process information/money for cleanup of their site, help them prepare and submit eligibility forms or request TAB or DBAC services for sites. | Review state website and other sites (databases) for updated information on any locally relevant cleanup of contaminated sites. | Review site inventory to identify candidate sites for reuse. | Prioritize sites on CVTC brownfield inventory: CVTC Land Use Committee recommendations developed and Council review/edit/approval of prioritized list. | For the top five prioritized sites on the CVTC brownfield inventory: quarterly information gathering (if possible; minimum annual information gathering) including one on one interviews with local community members and other knowledgeable individuals; visit sites to develop written and photographic documentation of site conditions, and document location with GPS; discuss sites with STRP colleagues (including DEC, etc.) for final determination of land status. | Occasionally attend Community Council meetings (Sutton, Chickaloon, Palmer) to learn about any areas of concern pertaining to BF issues. Do one brief presentation about brownfields during a meeting. | Continue gathering GPS data for brownfield and potential brownfield sites and incorporate them into the official site inventory and ArcGIS map. Use the ArcGIS map tool to accurately position data points on Mat-Su Borough property parcels in order to track potential responsible parties. | Use developed flow chart and associated written description of CVTC processes and tasks that are initiated with the report of a suspected or known contaminated site to cross-train staff in TRP management in order to prevent gaps in the program. | Continue our partnership with Native Village of Eklutna in working on sites in our overlapping area. We will compare databases and work together on joint sites of concern. | Continue to update digital tracking system which includes location, GPS points, landowner name, suspected or known contaminants, history of contamination, contact information for people with knowledge of the site, and a list of other resources specific to the site. | Continue updating CVTC inventory with suspected or known contaminated sites, including use of a digital mapping system of the site inventory to visually (and geographically) explain sites of concern. | Present to coworkers about Tribal Response Program and brownfield sites. | Conduct one on one interviews with local community members about potential brownfield sites (as possible due to pandemic concerns and CVTC pandemic protocols, should the pandemic be ongoing).
FY23 | Update a website or tracking system (Excel, paper files, etc.) with estimated or known BF sites. | Follow up with community members on sites of interest or concern (as available) | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | For community members that request process information/money for cleanup of their site, help them prepare and submit eligibility forms or request TAB or DBAC services for sites. | Review state website and other sites (databases) for updated information on any locally relevant cleanup of contaminated sites. | Review site inventory to identify candidate sites for reuse. | Prioritize sites on CVTC brownfield inventory: CVTC Land Use Committee recommendations and Council review/edit/approval of prioritized list. | For the top five prioritized sites on the CVTC brownfield inventory: quarterly information gathering (if possible; minimum annual information gathering) including one on one interviews with local community members (as available) and other knowledgeable individuals; visit sites to develop written and photographic documentation of site conditions, and document location with GPS; discuss sites with STRP colleagues (including DEC, etc.) for final determination of land status. | Occasionally attend Community Council meetings (Sutton, Chickaloon, Glacierview) to learn about any areas of concern pertaining to BF issues. Do one brief presentation about brownfields during a meeting. Garner information from those in attendance on the location of potential brownfield sites in the area. | Continue gathering GPS data for brownfield and potential brownfield sites and incorporate them into the official site inventory. Use the ArcGIS map tool or Google Earth Pro to accurately position data points on Mat-Su Borough property parcels in order to track potential responsible parties. | Use developed flow chart and associated written description of CVTC processes and tasks that are initiated with the report of a suspected or known contaminated site to cross-train staff in TRP management in order to prevent gaps in the program. | Continue our partnership with Native Village of Eklutna in working on sites in our overlapping area. We will compare databases and work together on joint sites of concern. | Continue updating CVTC inventory with suspected or known contaminated sites, including use of a digital mapping system of the site inventory to visually (and geographically) explain sites of concern. |  | Present to coworkers about Tribal Response Program and brownfield sites. | Conduct one on one interviews with local community members about potential brownfield sites as needed (if possible). | Alternately, keep track of any anonymous brownfield reports that come in through the website.
FY24 | Update a website or tracking system (Excel, paper files, etc.) with estimated or known BF sites. | Follow up with community members on sites of interest or concern (as available) | Visit sites, provide written and photographic documentation of site conditions, and capture location with GPS. (As needed). | For community members that request process information/money for cleanup of their site, help them prepare and submit eligibility forms or request TAB or DBAC services for sites. | Review state website and other sites (databases) for updated information on any locally relevant cleanup of contaminated sites. | Review E1 site inventory to identify candidate sites for reuse. | Prioritize sites on CVTC E1 site inventory using developed rubric in addition to: CVTC Land Use Committee recommendations and Council review/edit/approval of prioritized list. | For the top five (5) prioritized sites on the CVTC brownfield E1 site inventory: quarterly information gathering (if possible; minimum annual information gathering) including one-on-one interviews with local community members (as available) and other knowledgeable individuals; visit sites to develop written and photographic documentation of site conditions, and document location with GPS; discuss sites with STRP colleagues (i.e. DEC, ANTHC, CCLR, etc.) for final determination of land status. | Occasionally attend local Community Council meetings (e.g. Chickaloon, Sutton, Fishhook, etc.) to learn about any areas of concern pertaining to brownfield issues. If possible, give a short (5 min) overview of the STRP. Garner information from those in attendance on the location of potential brownfield sites in the area. | Continue gathering GPS data for brownfield and potential brownfield sites and incorporate them into the official site inventory. | Use developed flow chart and associated written description of CVTC processes and tasks that are initiated with the report of a suspected or known contaminated site to cross-train staff in TRP management in order to prevent gaps in the program. | Continue our partnership with Native Village of Eklutna in working on sites in our overlapping area. We will compare databases and work together on joint sites of concern. | Continue updating CVTC inventory with suspected or known contaminated sites, including use of a digital mapping system of the site inventory to visually (and geographically) explain sites of concern. |  | Present to coworkers about the Tribal Response Program and brownfield sites. | Conduct one-on-one interviews with local community members about potential brownfield sites as needed (if possible). | Alternately, keep track of any anonymous brownfield reports that come in through the website. | Use the ArcGIS map tool (or other acceptable mapping tool) to accurately position data points on Mat-Su Borough property parcels in order to track potential responsible parties. | Evaluate rubric for site prioritization scoring for updates if required (annually, at minimum).
FY25

## Element 2
Element 2 Activities
FY19 | Review ordinances that are in place and make suggestions for revisions. Work on ordinances and policies for Tribe to prevent and/or properly handle contamination. Work to draft procedures with department directors. Bring drafts of Tribal ordinances or policies to Council for approval.
FY20 | Schedule quarterly meetings with AK DEC to discuss the CVTC brownfield inventory and related topics | Attend trainings on Phase I and Phase II Environmental Site Assessments | Work with other CVTC departments to develop procedures and/or policies to prevent and prepare to handle contamination from spills, etc. | Continue learning best practices for clean ups and new ways to clean contaminated sites (e.g. webinars, conferences, articles, sign-up for relevant email lists) |  | Participation in CVTC Land Use Committee to share TRP information, stay aware of potential threats of contamination, and to provide comment letters regarding potential environmental threats as directed by the Tribal Council. |  |  | Attend the Alaska STRP Workshop (April) and Alaska Tribal Conference on Environmental Management (ATCEM) (November) to network with and learn from State and Tribal Response Programs in Alaska. | Maintain and update TRP Manual to keep any potential staff change-over as smooth as possible to prevent disruption to the program. | Cross training of other CVTC staff members so that all knowledge from TRP program will not be lost in any possible staff change.
FY21 | Schedule quarterly meetings with AK DEC to discuss public record as updated by DEC and concerns about contaminated sites | Attend trainings on how to write Phase I Environmental Site Assessments |  | Continue learning best practices for clean ups and new ways to clean contaminated sites (e.g. webinars, conferences, articles, sign-up for relevant email lists) | Ensure that CVTC departments (e.g. Transportation, Facilities) receive spill response training both for new staff and as a refresher | Participation in CVTC Land Use Committee with CVTC Staff, Executive Director, and Tribal Council Representative(s) to share TRP information, stay aware of potential threats of contamination, and to provide comment letters regarding potential environmental threats as directed by the Tribal Council. | Review DEC documents on contaminated sites and question actions they take (and those they don’t take) and write official letters as directed by Tribal Council. | Monitor DEC database and request to be contacted in case of a spill. | Attend the Alaska STRP Workshop (April) and Alaska Tribal Conference on Environmental Management (ATCEM) (November) to network with and learn from State and Tribal Response Programs in Alaska.
FY22 | Continue to stay in touch with AK DEC (our state enforcement agency) staff, by scheduling quarterly meetings to discuss contaminated sites in their database, the CVTC brownfield inventory, and related topics. | Attend training on Phase I and Phase II Environmental Site Assessments to stay current. | Research various assessment and clean up opportunities including, the Alaska Department of Environmental Conservation Brownfield Assessment and Cleanup and Targeted Brownfield Assessments. | Engage in quarterly meetings (or at least one annually) with Native Village of Eklutna or Sitka Tribe to see how they implement Element 2 in their TRPs | Ensure that CVTC departments (e.g. Transportation, Facilities) receive spill response training both for new staff and as a refresher. | Participate in CVTC Land Use Committee with CVTC Staff, Executive Director, and Tribal Council Representative(s) to share TRP information, stay aware of potential threats of contamination, and to provide comment letters regarding potential environmental threats as directed by the Tribal Council. | Review DEC documents on contaminated sites and evaluate actions they take (and those they don’t take) and write official letters as directed by Tribal Council. | Learn about contaminated site assessments and clean ups as well as new ways to clean contaminated sites (attend webinars and conferences like ITEP’s Tribal Lands and Environment Forum, read articles, and sign up for relevant email lists). | Review existing Tribal codes and ordinances and then suggest edits to be brought to the Tribal Council. | Work with other CVTC departments (e.g. Transportation and Facilities) to develop procedures and/or policies to prevent and prepare to handle contamination from spills, etc. | Using the CVTC site inventory and ArcGIS map, reach out to private property owners regarding brownfield or potential brownfield contamination on their property and offer guidance on how to clean it up before the Department of Environmental Conservation (DEC: Alaska’s enforcement authority) gets involved.
FY23 | Engage in quarterly meetings (or at least one annually) with Native Village of Eklutna or Sitka Tribe to see how they implement Element 2 in their TRPs | Attend training on Phase I and Phase II Environmental Site Assessments to stay current. | Research various assessment and clean up opportunities including, the Alaska Department of Environmental Conservation Brownfield Assessment and Cleanup and Targeted Brownfield Assessments. | Continue to stay in touch with AK DEC (the state enforcement agency) staff, by scheduling quarterly meetings to discuss contaminated sites in their database, updated to the CVTC brownfield inventory, and related topics. | Review the CVTC Public Record for any sites that have institutional controls (ICs). Visit sites in the winter months and again in summer months and review the state of the ICs. | Participate in CVTC Land Use Committee with CVTC Staff, Executive Director, and Tribal Council Representative(s) to share TRP information, stay aware of potential threats of contamination, and to research and draft comment letters regarding potential environmental threats as directed by the Tribal Council. | Review DEC documents on contaminated sites and evaluate actions they take (and those they don’t take) and write official letters as directed by Tribal Council. | Learn about contaminated site assessments and clean ups as well as new ways to clean contaminated sites (attend webinars and conferences like ITEP’s Tribal Lands and Environment Forum, read articles, and sign up for relevant email lists). | Review DEC documents on contaminated sites and evaluate actions they take (and those they don’t take) and write official letters as directed by Tribal Council. | Monitor DEC database and request to be contacted in case of a spill in our TRP area. | Using the CVTC site inventory and map, reach out to private property owners regarding brownfield or potential brownfield contamination on their property and offer guidance on how to clean it up before the Department of Environmental Conservation (DEC: Alaska’s enforcement authority) gets involved. | Attend at least one (1) Alaska Regional Response Team Meeting (ARRT) to stay apprised of how local, state, and federal agencies prepare and participate in response to pollution incidents. | Attend at least (1) Alaska Inland Area Committee (AIAC) or Arctic and Western Alaska (AAWA) meeting to stay apprised of how the operational plan for ADEC and USEPA responders is updated.
FY24 | Engage in quarterly meetings (or at least one annually) with Native Village of Eklutna or Sitka Tribe to see how they implement Element 2 in their TRPs | Attend training on Phase I and Phase II Environmental Site Assessments to stay current. | Research various assessment and clean up opportunities including, the Alaska Department of Environmental Conservation Brownfield Assessment and Cleanup and Targeted Brownfield Assessments to earn qualified sampler hours following DEC guidelines. | Continue to stay in touch with AK DEC (the state enforcement agency) staff via email correspondence or by scheduling quarterly meetings to discuss contaminated sites in their database, updated to the CVTC brownfield inventory, and related topics. | Review the CVTC Public Record for any sites that have institutional controls (ICs). Visit sites in the winter months (if accessible) and again in summer months and review the state of the ICs. Report findings to assigned DEC Contaminated Sites staff. | Participate in CVTC Land Use Committee with CVTC Staff, Executive Director, and Tribal Council Representative(s) to share TRP information, stay aware of potential threats of contamination, and to research and draft comment letters regarding potential environmental threats as directed by the Tribal Council. | Review DEC documents on contaminated sites and evaluate actions they take (and those they don’t take) and write official letters as directed by Tribal Council. | Learn about contaminated site assessments and clean ups as well as new ways to clean contaminated sites (attend webinars and conferences like ITEP’s Tribal Lands and Environment Forum, read articles, and sign up for relevant email lists). | Write SOP for CVTC Staff (etc.) for how to report a spill following ADEC guidelines. Include the creation of a spill report and where that report will be housed internally once completed. | Monitor DEC database and request to be contacted in case of a spill in our TRP area. | Request list of current Conditional Use Permits (CUPs) from Mat-Su Borough of permitted junk/scrap yards. | Using the CVTC site inventory and map, reach out to private property owners regarding brownfield or potential brownfield contamination on their property and offer guidance on how to clean it up before the Department of Environmental Conservation (DEC: Alaska’s enforcement authority) gets involved. | Compare these properties to aerial map of properties with this kind of pollution. Properties without a CUP in place should be reported to MSB Code Compliance if outreach efforts are not successful (and supervisor agrees). | Attend at least one (1) Alaska Regional Response Team Meeting (ARRT) to stay apprised of how local, state, and federal agencies prepare and participate in response to pollution incidents. | Attend at least (1) Alaska Inland Area Committee (AIAC) or Arctic and Western Alaska (AAWA) meeting to stay apprised of how the operational plan for ADEC and USEPA responders is updated. | Attend relevant meetings to stay apprised of how local, state, and federal agencies are preparing to regulate contamination and cleanup of “emerging contaminants of concern” (e.g. PFAS, etc.) as they write laws.
FY25

## Element 3
Element 3 Activities
FY19 | Outreach projects with local schools to increase awareness and prevention of future contaminated sites. | Conduct outreach at community events (Annual Tribal Gathering for example). | Participate in public meetings that are relevant to help engage with community. | Outreach materials for dissemination at local community sites (Library, Post Office, Health Clinic, Schools…) | Update and maintain outreach materials as needed.
FY20 | Outreach projects with local schools to increase awareness and prevention of future contaminated sites, and to possible record new sites of interest on inventory. | Conduct outreach at community events (e.g. Annual Gathering, Sutton Safety Expo, etc.) to increase awareness of brownfields and contamination prevention | Participate in community council meetings (Sutton, Chickaloon, Palmer) that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. | Participate in meetings with local clubs that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. Examples: Kiwanis, Mat-Su Dirt Fishers (Metal Detectorists), Jeep/OHV/ATV clubs, etc. | Update outreach materials as necessary and maintain resource of outreach materials at community locations, such as: post office, library, community health clinic. | Present to coworkers and community members about TRP project and brownfield sites. | Maintain regular outreach method for announcements and/or updates to public (Instagram: @brownfieldbear; Nen’ eł Tuu Newsletter) | Collaborate with other organizations that will share our materials and refer people to us for information, such as local recycling center. | Respond to community concerns about contamination as needed. | Keep CVTC’s TRP Public Record updated for the community and public to access. | Maintain TRP information and TRP Coordinator contact information on the CVTC website. | Maintain fillable form on website for community members to enter sites of concern.
FY21 | Outreach projects such as presentations (e.g. brownfields) or demonstrations (e.g. how to clean up very small oil spills with cornstarch), or solicitiations of student work to put in newsletter (e.g. articles, drawings, photos, cartoons pertaining to cleaning up the environment and reusing the land) local schools (e.g. YNDA School, Sutton Elementary) to increase awareness and prevention of future contaminated sites, and to possible record new sites of interest on inventory. To be completed biannually if not more often. | Conduct outreach at community events (e.g. Annual Gathering, Sutton Safety Expo, etc.) to increase awareness of brownfields and contamination prevention | Participate in community council meetings (Sutton, Chickaloon, Palmer) that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. Task to be performed at least once quarterly if not more often. |  | Update outreach materials as necessary and maintain resource of outreach materials at community locations, such as: post office, library, community health clinic. | Create new outreach material: · Overview of selected TRP topics · Prioritization of contaminated sites · Reuse ideas for sites identified for cleanup CVTC site inventory explanation for public who have questions when observing TRP Coordinator recording local sites that may be contaminated. | Maintain regular outreach method for announcements and/or updates to public: · Instagram: @brownfieldbear · Nen’ eł Tuu Newsletter · CVTC Newsletter | Collaborate with other organizations that will share our materials and refer people to us for information, such as local recycling center. | Respond to community concerns about contamination as needed. | Keep website updated with TRP Public Record for community and public to access. | Maintain TRP information and TRP Coordinator contact information on the CVTC website. | Maintain fillable form on website for community members to enter sites of concern. | Present to LUC members about TRP project and brownfield sites. At separate meetings: · Overview of selected TRP topics · Prioritization of contaminated sites · Reuse ideas for sites identified for cleanup
FY22 |  | Conduct outreach at community events (e.g. Annual Gathering, Sutton Safety Expo, etc.) to increase awareness of brownfields and contamination prevention | Participate in community council meetings (Sutton, Chickaloon, Palmer) that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. |  | Update outreach materials as necessary and maintain resource of outreach materials at community locations, such as: post office, library, community health clinic. |  | Maintain regular outreach method for announcements and/or updates to public: Instagram: @brownfieldbear; Nen’ eł Tuu Newsletter; CVTC Newsletter | Collaborate with other organizations that will share our materials and refer people to us for information, such as local recycling center. | Respond to community concerns about contamination as needed. | Maintain TRP information and TRP Coordinator contact information on the CVTC website and keep website updated with TRP Public Record for community and public to access. |  |  | Present to LUC members about TRP project and brownfield sites. At separate meetings: · Overview of selected TRP topics · Prioritization of contaminated sites · Reuse ideas for sites identified for cleanup | Participate in the National Tribal Brownfields Working Group (NTBFWG). | Create new workflow for TRP manual describing steps to take when responding to reports received by community members via on-line fillable form.
FY23 |  | Conduct outreach at community events (e.g. Annual Gathering, Sutton Safety Expo, etc.) to increase awareness of brownfields and contamination prevention | Participate in occasional community council meetings (Sutton, Chickaloon, Glacierview) that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. |  | Update outreach materials as necessary and maintain resource of outreach materials at community locations, such as: post office, library, community health clinic. |  | Maintain regular outreach method for announcements and/or updates to public: Instagram: @brownfieldbear; Nen’ eł Tuu Newsletter; CVTC Newsletter | Collaborate with other organizations that will share our materials and refer people to us for information, such as the local recycling center, libraries, and museums. | Respond to community concerns about contamination as needed, including anonymous community brownfield reports (if they provide contact information), | Maintain TRP information and TRP Coordinator contact information on the CVTC website. |  |  |  |  | Participate in the Sutton Community Hall Working Group (SCHWG). | Create new workflow for TRP manual describing steps to take when responding to reports received by community members via on-line fillable form. | Participate in the National Tribal Brownfields Working Group (NTBWG).
FY24 |  | Conduct outreach at community events (e.g. Annual Gathering, Wasilla Museum, ADF&G, Mat-Su Fiber Festival, etc.) to increase awareness of brownfields and contamination prevention. | Participate in occasional community council meetings (Sutton, Chickaloon, Glacier View, Fishhook, etc.) that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. |  | Update outreach materials as necessary and maintain resource of outreach materials at community locations, such as: post office, library, community health clinic. |  | Maintain regular outreach method for announcements and/or updates to public: Instagram: @brownfieldbear; Nen’ eł Tuu Newsletter. | Collaborate with other organizations that will share our materials and refer people to us for information, such as the local recycling center, libraries, and museums. | Respond to community concerns about contamination as needed, including anonymous community brownfield reports (if they provide contact information), | Maintain TRP information and TRP Coordinator contact information on the CVTC website. | Participate in pertinent Mat-Su Borough Assembly meetings that are relevant (contaminated sites/brownfields/spill prevention, etc.) in order to help engage with community. | Participate in the Northwest Brownfields Peer Group (NBPG - CCLR, R10). | Continue to lead the Sutton Community Hall Working Group (SCHWG) as we work on the former Sutton Community Hall site.
FY25

## Element 4
Element 4 Activities
FY19 | Partner with Native Village of Eklutna to work with them and learn alongside them on their site work (NALEMP). | When possible, include TRP Coordinator in any related contamination assessment or cleanup work in the CVTC traditional territory. | TRP will be trained or refreshed in Water and Soil Sampling. | Actively search for organizations that might serve as a mentor for earning hours in the field. | Attendance of webinars and review of research on cleanups and methods. | Keep an eye on any local cleanups and cleanup events.
FY20 | Partner with Native Village of Eklutna to work with them and learn alongside them on their site work (NALEMP). | When possible, TRP Coordinator is to be included in any related contamination assessment or cleanup work in the CVTC traditional territory. | TRP Coordinator will be trained/refreshed in Water and Soil Sampling. | Actively search for organizations that might serve as a mentor for earning hours in the field. | Attendance of webinars and review of research on cleanups and methods. | TRP Coordinator to keep abreast of any local cleanups/cleanup events.
FY21 |  | When possible, TRP Coordinator is to be included in any related contamination assessment or cleanup work in the CVTC traditional territory. | TRP Coordinator will be trained/refreshed in Water and Soil Sampling. | TRP Coordinator will shadow a qualified sampler for the required number of hours to maintain the “qualified sampler” qualification. | Attendance of webinars and review of research on cleanups and methods. | TRP Coordinator to keep abreast of any local cleanups/cleanup events. To involve DEC staff quarterly to request information on any local site cleanups that are planned, and permission to watch/participate.
FY22 |  | When possible, TRP Coordinator is to be included in any related contamination assessment or cleanup work in the CVTC traditional territory. | TRP Coordinator will be refreshed in Water and Soil Sampling. | Actively search for organizations that might serve as a mentor for earning hours in the field; 30-hours of field observation are required in addition to coursework to earn Qualified Sampler Status. This may be done by coordinating with the Alaska Native Tribal Health Consortium’s pilot program which seeks to pair companies (mentors) with samplers needed fieldwork (mentees). | Attendance of webinars and review of research on cleanups and methods. | TRP Coordinator to keep abreast of any local cleanups/cleanup events. To involve DEC staff quarterly to request information on any local site cleanups that are planned, and permission to watch/participate.
FY23 |  | When possible, TRP Coordinator is to be included in any related contamination assessment or cleanup work in the CVTC traditional territory. | TRP Coordinator will be refreshed in Water and Soil Sampling. | Actively search for organizations that might serve as a mentor for earning hours in the field; 30-hours of field observation are required in addition to coursework to earn Qualified Sampler Status. This may be done by coordinating with the Alaska Native Tribal Health Consortium’s pilot program which seeks to pair companies (mentors) with samplers needed fieldwork (mentees). | Attendance of webinars and review of research on cleanups and methods. | TRP Coordinator to keep abreast of any local cleanups/cleanup events. To involve DEC staff quarterly to request information on any local site cleanups that are planned, and permission to watch/participate. | Review existing Tribal codes and ordinances regarding cleanups and then suggest edits to be brought to the Tribal Council. | Review state website and other sites (databases) for updated information on any locally relevant cleanup of contaminated sites.
FY24 |  | When possible, TRP Coordinator is to be included in any related contamination assessment or cleanup work in the CVTC traditional territory. (This also counts towards Qualified Sampler hours.) | TRP Coordinator will be refreshed in Water and Soil Sampling. | Actively search for organizations that might serve as a mentor for earning hours in the field; 480-hours of field observation are required in addition to coursework to earn Qualified Sampler Status. This may be done by coordinating with the Alaska Native Tribal Health Consortium’s pilot program which seeks to pair companies (mentors) with samplers needed fieldwork (mentees). | Attendance of webinars and review of research on cleanups and methods. | TRP Coordinator to keep abreast of any local cleanups/cleanup events. To involve DEC staff quarterly to request information on any local site cleanups that are planned, and permission to watch/participate. | Review existing Tribal codes and ordinances regarding cleanups and then suggest edits to be brought to the Tribal Council. | Review state website and other sites (databases) for updated information on any locally relevant cleanup of contaminated sites. | TRP Coordinator will be refreshed in 40-hr HAZWOPER training (annually) to ensure safety while physically present on (suspected) brownfield sites for monitoring/sampling purposes. | Participate in Area Committee Meetings (AIAC, ARRT, AWA) and provide comments on plan updates or policy guidance if applicable. | Continue DEC Contaminated Sites Staff quarterly correspondence for sites that are being updated to “cleanup complete” in the Public Record. | Participate in ANCSA meetings (hosted by ANTHC and DEC) and look for ways the TRP can be involved with our regional office (CMCRC) to get contaminated conveyed lands restored.
FY25